## Project Planner
Gouda Squad Asset List
| Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Week Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
CATAGORY | ACTIVITY | ASSIGNED TO | Week Start | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEK
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Enviornments
Buildings
| Building short: Shop | Maddie | 6 | 1 | 6 | 1 | 0%
| Building short: Open Market | Maddie | 6 | 1 | 6 | 1 | 0%
| Building: Parking Garage | Michael | 6 | 1 | 6 | 1 | 0%
| Building tall: Base 1 | Michael | 6 | 1 | 6 | 1 | 0%
| Modular Storefront 1 | Michael | 6 | 1 | 6 | 1 | 0%
| Modular storefront 2 | Maddie | 7 | 1 | 7 | 1 | 0%
| Modular storefront 3 | Maddie | 7 | 1 | 7 | 1 | 0%
| Guard Towers | Michael | 6 | 1 | 7 | 1 | 0%
Walls/floors
| Wall straight | Maddie | 7 | 1 | 7 | 1 | 0%
| Wall Vertical | Maddie | 7 | 1 | 7 | 1 | 0%
| Street 90 degree | Michael | 6 | 1 | 6 | 1 | 0%
| sidewalk 90 degree | Michael | 7 | 1 | 6 | 1 | 0%
| fence straight | Michael | 7 | 1 | 6 | 1 | 0%
| Fence Vertical | Michael | 7 | 1 | 6 | 1 | 0%
Hero Buildings
| Goal Building | Michael | 11 | 1 | 8 | 1 | 0%
Characters
Turn Arounds
| Gui | Sarai | 6 | 2 | 6 | 2 | 0%
| Altereds | Sarai | 8 | 1 | 8 | 1 | 0%
| Naturals | Sarai
| Synths | Sarai
Final
| Gui | Sarai | 11 | 1 | 11 | 1 | 0%
| Altereds | Sarai | 11 | 1 | 11 | 1 | 0%
| Naturals | Sarai
| Synths | Sarai
Color
| Gui | Sarai | 6 | 1 | 6 | 1 | 0%
| Altereds | Sarai | 6 | 1 | 6 | 1 | 0%
| Naturals | Sarai
| Synths | Sarai
Breaking up for rigging
| Gui | Sarai | 13 | 1 | 13 | 1 | 0%
| Altereds | Sarai | 13 | 1 | 13 | 1 | 0%
| Naturals | Sarai
| Synths | Sarai
Props
Concepts
| Snow Piles | Michael | 7 | 1 | 7 | 1 | 0%
| Street Signs | Maddie | 9 | 1 | 9 | 1 | 0%
| Street lights | Maddie | 9 | 1 | 9 | 1 | 0%
| Crates | Michael | 11 | 1 | 8 | 1 | 0%
| Air Conditioner Wall | Maddie | 9 | 1 | 9 | 1 | 0%
| Blockade Street | Maddie | 9 | 1 | 9 | 1 | 0%
| Sign: circular | Michael | 11 | 1 | 8 | 1 | 0%
Sign: Angled Down
Camera
Table
Chair
Bulldozer
Manhole Cover
Pallet
Grafitti
Latter
Satelite Dish
Bridge
Boxes
FireHydrant
VFX
| Observe Ability | Michael | 8 | 1 | 7 | 1 | 0%
| Enemy Alerted | Michael | 8 | 1 | 8 | 1 | 0%
| Snowfall | Michael | 8 | 1 | 7 | 1 | 0%
Footsteps in Snow
Dash
Dust
Alarm
UI
Concepts
| HUD | Michael | 8 | 1 | 5 | 1 | 0%
| Main Menu | Michael | 8 | 1 | 8 | 1 | 0%
| Pause | Michael | 8 | 1 | 8 | 1 | 0%
Win
Fail
Controls
Settings
Credits
Animations
Animation
| Idle | andrew | 6 | 1 | 6 | 1 | 0%
| Move horizontal | andrew | 7 | 1 | 7 | 1 | 0%
| Move up | andrew | 8 | 1 | 8 | 1 | 0%
| Move Down | andrew | 9 | 1 | 9 | 1 | 0%
| Observe | andrew | 10 | 1 | 10 | 1 | 0%
| Dash | andrew | 11 | 1 | 11 | 1 | 0%
| Death | andrew | 12 | 1 | 12 | 1 | 0%
Splash Art
Concepts
| Characters | Sarai |  | 1 |  | 1 | 0%
| Environment | Michael |  | 1 |  | 1 | 0%
| Props | Maddie |  | 1 |  | 1 | 0%
| Layout | All |  | 1 |  | 1 | 0%
Final Assets
| Characters | Sarai |  | 1 |  | 1 | 0%
| Environment | Michael |  | 1 |  | 1 | 0%
| Props | Maddie |  | 1 |  | 1 | 0%
| Layout | All |  | 1 |  | 1 | 0%